## SE(Dron)
DETAILS OF THIRD PARTY QUALITY AUDITORS FOR SE(DRON) CIRCLE (INFRA WORKS)
DIVISION : EE(Dron-I)
Sr. No. | Name of Work / Agency / C.A. No. | Date of Start | Awarded Value / Revised Value (Rs. In Lacs) | Name of TPQA Agency / C.A.No. of TPQA work | Date of Appointment | Rate per visit(Rs) | No. of visits |  | Remarks
Date of Comple./ Extended date of Completion
| Reclamation of Proposed Metro Depot Plot No.10 at Dronagiri. C.A.04 /CIDCO/EE (Dron –I )/13-14 Agency:- M/s.Shreeniwasa Constructions Pvt.Ltd. | 17.02.2014
16.02.2014
[7 empty] | Planned | Actual
1 | Integrated Development of Physical Infrastructure works in Sectors 52 to 55 under 12.5% scheme at Dronagiri. C.A.06/CIDCO/EE (Dron –I )/13-14 Agency: M/s J.M.Mhatre Infra Pvt.Ltd. | 09.01.2014/ 08.01.2016 | 3622 | M/s. Certification Engineers International Ltd./ C.A.No.8©/CIDCO/ SE(HQ)/EE(NM)/2013-14 | 07.01.2014 | 19107 | 15 | 2
2 | Construction Of S.W.Drain & Development of Foothpath along 36M road from Balmer Lawrie to BPCL at Dronagiri. C.A.07/CIDCO/EE (Dron –I )/13-14 Agency: M/s. K.D.Constructions Pvt.Ltd. | 04.03.2014/ 03.03.2015 | 692 | M/s. Structwell Consultants Pvt.Ltd./ C.A.No.C.A.No.8(A)/CIDCO/ SE(HQ)/EE(NM)/ 2013-14 | 07.01.2014 | 19107 | 5 | 1
DIVISION : EE(Dron-II)
1 | Construction of roads upto 1st stage of asphalting including storm water drains, water supply lines and balance sewer lines in Sect-27 under 12.5% at Dronagiri. / M/s Thakur Infraprojects Pvt. Ltd. / 01/CIDCO/EE(DRON-II)/2013-14. | 09/12/2013/ 08/12/2015 | 1631.03 | M/s. Shirkhande consultants Pvt. Ltd. C.A.No-C.A.No.8(B)/CIDCO/ SE(HQ)/EE(NM)/2013-14 | 07.01.2014 | 19107 | 10 | 3
2 | Construction of roads up to 1st stage of asphalting including storm water drains & balance sewer line works, in Sectors 47 & 48 under 12.50% scheme at Dronagiri. / M/s P. P. Kharpatil Construction Pvt. Ltd./ 02/CIDCO/EE (DRON-II)/2013-14. | 24/10/2013/ 23/10/15 | 1516 | M/s. Shirkhande consultants Pvt. Ltd. C.A.No-C.A.No.8(B)/CIDCO/ SE(HQ)/EE(NM)/2013-14 | 07.01.2014 | 19107 | 15 | 3
3 | Construction of roads up to 1st stage of asphalting including storm water drains & balance sewer lines works, channel & along with box type culvert in sector 56 & 59 under 12.5% scheme at Dronagiri. / M/s. J. M. Mhatre / 03/CIDCO/ EE(DRON-II)/2013-14. | 16/07/2013/ 15/07/2014 | 2025 | M/s. Certification Engineers International Ltd./ C.A.No.8©/CIDCO/ SE(HQ)/EE(NM)/2013-14 | 07.01.2014 | 19107 | 10 | 4
4 | Construction of Roads upto Ist. Stage of Asphalting including Storm Water Drains, Water Supply lines & balance Sewer line work in Sector- 15 under 12.50 % at Dronagiri. M/s VUB Engineering Pvt. Ltd. C.A.No.04/CIDCO/EE(DRON-II)/ 2013-14 | 19/12/2013 18/12/2015 | 1334.29 | M/s. Structwell Consultants Pvt.Ltd./ C.A.No.C.A.No.8(A)/ CIDCO/ SE(HQ)/EE(NM)/2013-14 | 07.01.2014 | 19107 | 2 | 1
DIVISION : EE(Dron-III)
1 | Strengthening / Resurfacing of Arterial 36m wide road from Khopta Bridge to IOTl in Sector-1 at Dronagiri, Navi Mumbai. C.A.No.03/CIDCO/EE(Dron-I)/13-14 Agency :- | 17/12/2013 15/06/2015 | 3301.9 | M/s. Structwell Consultants Pvt.Ltd./ C.A.No.C.A.No.8(A)/CIDCO/ SE(HQ)/EE(NM)/2013-14 | 07.01.2014 | 19107 | 15 | 7
2 | Construction of Compound wall for Proposed Crematorium & Burial ground in Sector-51 A, at Dronagiri, Navi Mumbai. C.A.No.01/CIDCO/EE(Dron-III)/13-14. Agency :- L.T.Patil & Bros. | 03/02/2014 02/02/2015 | 184.62 | M/s. Certification Engineers International Ltd./ C.A.No.8©/CIDCO/ SE(HQ)/EE(NM)/2013-14 | 07.01.2014 | 19107 | 5 | 3
3 | Integrated development of physical infrastructure works in sector-50 & 51 under 12.5% scheme at Dronagiri. M/s. Thakur Infraprojects (P) Ltd. 05/CIDCO/EE(Dron-I)/13-14 | 19/12/2013 18/12/2015 | 1784.77 | M/s. Shirkhande consultants Pvt. Ltd. C.A.No-C.A.No.8(B)/CIDCO/ SE(HQ)/EE(NM)/2013-14 | 07.01.2014 | 19107 | 10 | 2
4 | Development of parking space for temporary parking and for unauthorized vehicles in Dronagiri Node. C. A. No. 05/CIDCO/EE (DRON-III)/13-14 Agency: M/s P. P. Kharpatil Construction Pvt. Ltd. | 29/05/2014 28/02/2015 | 246.8127 | M/s. Structwell Consultants Pvt.Ltd./ C.A.No.C.A.No.8(A)/CIDCO/ SE(HQ)/EE(NM)/2013-14 | 07.01.2014 | 19107 | 3 | 1
41.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.0

## SE(Ulwe)
DETAILS OF THIRD PARTY QUALITY AUDITORS FOR SE(ULWE) CIRCLE (INFRA WORKS)
DIVISION : EE(Ulwe-I)
Sr. No. | Name of Work / Agency / C.A. No. | Date of Start | Awarded Value / Revised Value (Rs. In Lacs) | Name of TPQA Agency / C.A.No. of TPQA work | Date of Appointment | Rate per visit(Rs) | No.of visits |  | Remarks
Date of Comple./ Extended date of Completion
[7 empty] | Planned | Actual
1 | Integrated development of infrastructural works of balance roads (upto stage-I), S.W. Drains, etc. in Sector-20 & 21 of 12.5% scheme at Ulwe, Navi Mumbai. C.A. No.01/CIDCO/SE(Ulwe) /EE(Ulwe-I)/2012-13 Agency :-M/s K.D. Construction Pvt Ltd. | 05.02.2013/ 04.08.2014 | 714.35/ 711.85 | M/s. Certification Engineers International Ltd./ C.A.No.9(A)/CIDCO/SE(HQ)/ EE(NM)/ 2013-14 | 04.06.2014 | 24800 | 1 | 1
2 | Integrated development of infrastructural works of balance roads (up to stage–I), S.W. Drain, Sewerage & water supply lines etc. in Sector-2, 3 & 5 of 12.5% scheme at Ulwe, Navi Mumbai. C.A.No.: 02/CIDCO/SE(Ulwe) /EE(Ulwe-I)/2012-13 Agency:- M/s Girish Enterprises Pvt. Ltd. | 06.06.2013/ 05.12.2014 | 493.86 | M/s. Certification Engineers International Ltd./ C.A.No.9(A)/CIDCO/SE(HQ)/ EE(NM)/ 2013-14 | 04.06.2014 | 24800 | 4 | 2
3 | Integrated development of balance infrastructure owrks of road (upto stage-I), S.W. Drains, Sewerage and water supply etc. in Sector-23 under 12.5% scheme in Sector-23 at Ulwe, Navi Mumbai. C.A. No.03/CIDCO/SE(Ulwe) /EE(Ulwe-I)/2012-13 Agency :- M/s VUB Engineering Pvt Ltd. | 24.05.2013/ 23.11.2014/ 07.04.15(Proposal of extension under process) | 759.16 | M/s. Certification Engineers International Ltd./ C.A.No.03/CIDCO/ SE(HQ)/ EE(NM)/2013-14 | 11.09.2013 | 9800 | 7 | 4
4 | Integrated development of Infrastructural works for balance roads(Up to stage-I) ,S.W.drain,sewerage & water supply lines etc. in sector- 4,7 & 22 of 12.5% scheme at Ulwe ,Navi Mumbai C.A. No.01/CIDCO/SE(Ulwe) /EE(Ulwe-I)/2013-14 Agency :- M/s.Govardhani construction co. | 28.08.2014/ 27.08.2016 | 1092 | M/s. Certification Engineers International Ltd./ C.A.No.02/CIDCO/ SE(HQ)/ EE(NM)/2013-14 | 11.09.2013 | 9800 | 3
|  |  |  | M/s. Certification Engineers International Ltd., C.A.No-02/CIDCO/CE(South)/ 2013-14 | 11.09.2013 | 9800 | 5
5 | Construction & commissioning of 32 MLD sewerage Pump house in sector-22 including rising main at Ulwe ,Navi Mumbai C.A. No.02/CIDCO/SE(Ulwe) /EE(Ulwe-I)/2013-14 Agency :- M/s.J.M.Mhatre Infra.Pvt.Ltd. | 28.08.2014/ 27.08.2016 | 1972.8 | M/s Indian Register of shipping. C.A.No.9(B)/CIDCO/SE(HQ)/ EE(NM)/ 2013-14 | 12.05.2014 | 24800 | 5
|  |  |  | M/s Indian Register of shipping. C.A.No.01/CIDCO/SE(HQ)/ EE(NM)/ 2013-14 | 12.08.2013 | 82500 | 5
DIVISION : EE(Ulwe-II)
1 | P/L 800mm dia D.I. water supply feder main for Phase-II area from Amra marg to Sec-18, Ulwe C.A.No. 01/SE(Ulwe)/EE(UL-II)/12-13 Agency :-M/s. Thakur Infra Projects Pvt. Ltd. | 14.03.2013/ 13.06.2014 | 348.02/ 294.13 | M/s Indian Register of shipping. C.A.No.9(B)/CIDCO/SE(HQ)/ EE(NM)/ 2013-14 | 12.05.2014 | 24800 | 2 | 2
2 | Development of integrated infrastructure work under 12.5% in Sec 17 at Ulwe. C.A.No. 04/SE(Ulwe)/EE(UL-II)/12-13 Agency :-M/s. Thakur Infraprojects Pvt. Ltd. | 12.02.2013/ 10.02.2015 | 922.23/ 965.46 | M/s Indian Register of shipping. C.A.No.9(B)/CIDCO/SE(HQ)/ EE(NM)/ 2013-14 | 12.05.2014 | 24800 | 2 | 2
3 | Development of integrated infrastructure work under 12.5% in Sec 16 at Ulwe.C.A.No. 05/SE(Ulwe)/EE(UL-II)/12-13 Agency :-M/s. Thakur Infraprojects Pvt. Ltd. | 09.07.2013/ 08.07.2015 | 767.53 | M/s. Certification Engineers International Ltd./ C.A.No.02/CIDCO/ SE(HQ)/ EE(NM)/2013-14 | 11.09.2013 | 9800 | 7 | 4
4 | Process designing for 32 MLD STP in sector-6 at Ulwe. C.A.No. 02/SE(Ulwe)/EE(UL-II)/13-14 Agency :-M/s. Khilari Infrastructure Pvt.Ltd. | 19.08.2014/ 18.08.2016 | 4647.94 | M/s Indian Register of shipping. C.A.No:-13/CIDCO/SE(HQ) /EE(NM) /2013-14 | 26.05.2014 | 15300 | 12
5 | Integrtaed Infrastructure works under 12.5% scheme in sector- 8 at Ulwe C.A.No- 09/CIDCO/SE(Ulwe)/EE(UL-II)/2012-13 Agency :-M/s. Kailashchandra Deelipkumar const.Pvt.ltd | 20.08.2014/ 27.02.2016 | 798.2 | M/s Indian Register of shipping. C.A.No:-13/CIDCO/SE(HQ) /EE(NM) /2013-14 | 26.05.2014 | 15300 | 6
DIVISION : EE(Ulwe-III)
1 | Designing Planning and Construction of Commercial Complex in Sect-19A, Ulwe C.A.No.:- 01/CIDCO/ SE (Ulwe)/2011-12. Agency:- M/s. B.G. Shirke Construction Tech. Pvt. Ltd. | 06.12.2012/ 05.06.2014/ 18.10.2014 | 3471.77 3828.41 | M/s Indian Register of shipping. C.A.No.01/CIDCO/SE(HQ)/ EE(NM)/ 2013-14 | 12.08.2013 | 82500 | 8 | 8 |  | +
2 | Integrated Development of infrastructure works in sector-10B & construction of S.W.drains along 24 m & 15 m wide road in sector- 19B at Ulwe Node,Navi Mumbai C.A.No.:- 05/CIDCO/ SE (Ulwe)/EE(Ulwe-III)/2013-14. Agency:- M/s. Thakur Infraprojects Pvt.Ltd. | 14.08.2014/ 13.02.2016 | 1123.96 | M/s. Certification Engineers International Ltd./ C.A.No.9(A)/CIDCO/SE(HQ)/ EE(NM)/ 2013-14 | 12.08.2013 | 82500 | 9
|  |  |  | M/s. Certification Engineers International Ltd./ C.A.No.03/CIDCO/ SE(HQ)/ EE(NM)/2013-14 | 11.09.2013 | 9800 | 1
3 | Integrtaed Development of Infrastructure works under 12.5% scheme in sector-9 at Ulwe Node,Navi Mumbai C.A.No- 01/CIDCO/SE(Ulwe)/EE(UL-III)/2013-14 Agency :-M/s.Thakur Infraprojects Pvt.Ltd. | 14.08.2014/ 13.08.2016 | 2438.78 | M/s Indian Register of shipping. C.A.No:-13/CIDCO/SE(HQ) /EE(NM) /2013-14 | 26.05.2014 | 15300 | 12
41.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.0

## SE(KHR)
DETAILS OF THIRD PARTY QUALITY AUDITORS FOR SE(KHARGHAR) CIRCLE (INFRA WORKS)
DIVISION : EE(KHR-I)
Sr. No. | Name of Work / Agency / C.A. No. | Date of Start | Awarded Value / Revised Value (Rs. In Lacs) | Name of TPQA Agency / C.A.No. of TPQA work | Date of Appintment | Rate per visit(Rs) | No.of visits |  | Remarks
Date of Comple./ Extended date of Completion
[7 empty] | Planned | Actual
1 | Development of power supply infrastructure distribution network with construction of 33/11 KV HT substations and allied works in se-25 to 45, Kharghar node, Navi Mumbai (Phase-I). (Civil Part) Agency: M/s IVRCL Ltd. C.A.No-12/CIDCO/EE(Elect-I)/ 2011-12 | 30.08.2012/ 29.08.2014 | 1079.5 | M/s. Certification Engineers International Ltd. C.A.No. 14/CIDCO/SE(HQ)/ EE (NM)/2013-14 | 06.05.2014 | 24900 | 12 | 7
2 | Earth Filling in areas of Sector-25, Central Park at Kharghar C. A. No. 02/CIDCO/EE(KHR-I)/2013 – 14 Agency: M/s. Thakur Infraprojects Pvt. Ltd. | 02.01.2014 / 01.07.2014 | 638.31 | M/s. Structwel Designers & Consultants Pvt. Ltd. C.A.No-13/CIDCO/CE(S)/ 2013-14 |  |  | 1 | 1
DIVISION : EE(KHR-II)
1 | Training of existing Storm water Channel from Golf Course to Taloja Creek at Kharghar. Part –II. Ch. 900 to Ch. 3205. 05/CIDCO/EE(KHR-II)/12-13 M/s. Shree Venkateshwara Infrastructure Pvt. Ltd. | 12.02.2013/ 11.08.2014 | 1008.9 | M/s Indian Register of shiping. CIDCO/SE(KHR-I)/2013/1077 |  |  | 6 | 4
2 | Construction of approach road from Pandav Marg Taloja Junction to HSR plot in Sector – 22 at Kharghar. 12/CIDCO/EE(KHR-II)/12-13 M/s. Thakur Infra projects Pvt. Ltd. (TIPL) | 02.05.2013/ 02.08.2014 | 269.29 | M/s. Structwell Engineers & Consultants Pvt. Ltd. C.A.No-04/CIDCO/CE(S)/ 2013-14 |  |  | 1 | 1
3 | Development of Garden (Grahamandal) on plot No. 12 in Sector – 7 at Kharghar. 04/CIDCO/EE(KHR-II)/13-14 M/s. Bhairavnath Construction Co. | 19.12.2013 18.06.2014 Extension requested | 70.53 | M/s Indian Register of shiping. C.A.No:- 05/CIDCO/CE(S)/ 2012-13 |  |  | 2 | 2
4 | Development of Garden (Rainbow) on plot No. 8 in Sector – 2 at Kharghar. 11/CIDCO/EE(KHR-II)/13-14 M/s. Jai Malhar Enterprises | 19.12.13 18.06.14 Extension requested | 84.97 | M/s Indian Register of shiping. C.A.No:- 05/CIDCO/CE(S)/ 2012-13 |  |  | 2 | 2
5 | Development of Garden (Zodiac) on plot No. 41 in Sector – 19 at Kharghar. 01/CIDCO/EE(KHR-II)/13-14 M/s. BVG India Ltd. | 19.12.2013 18.12.2014 | 140.76 | M/s Indian Register of shiping. C.A.No:- 05/CIDCO/CE(S)/ 2012-13 |  |  | 2 | 2
6 | Integrated development of balance infra. Under 12.5% scheme in Sector – 19, Kharghar. 05/CIDCO/EE(KHR-II)/13-14 M/s. Govardhani Const. Co., | 21.01.2014 20.01.2015 | 258.39 | M/s. Structwell Engineers & Consultants Pvt. Ltd. C.A.No-04/CIDCO/CE(S)/ 2013-14 |  |  | 6 | 1
7 | Upgradation of Pravesh Marg, Pandav Marg & other 35m wide peripheral roads in Sector – 19, 20 & 21 at Kharghar. 13/CIDCO/EE(KHR-II)/13-14 M/s. VUB Engineering Pvt. Ltd. | 23.01.2014 22.05.2015 (excluding monsoon) | 469.46 | M/s. Structwell Engineers & Consultants Pvt. Ltd. C.A.No-04/CIDCO/CE(S)/ 2013-14 |  |  | 6 | 2
8 | Upgradation of roads in Sector – 2,3,4,5 & 8 at Kharghar. 15/CIDCO/EE(KHR-II)/13-14 M/s. Shree Krishna Const. | 27.01.2014 26.05.2015 | 458.2 | M/s. Structwell Engineers & Consultants Pvt. Ltd. C.A.No-04/CIDCO/CE(S)/ 2013-14
9 | Construction of box culvert on 20 m. wide road across 45 m wide channel in Sector – 11 at Kharghar. 22/ CIDCO/EE(KHR-II)/13-14 M/s. Shree Venkateshawara Infrastructure Pvt Ltd. | 24.02.2014 23.02.2015 | 336.53 | M/s Indian Register of shiping. |  |  | 6 | 1
10 | Const. of storm water channel along the front of Kharghar hill in Sector – 5, Kharghar. 18/CIDCO/EE(KHR-II)/13-14 | 25.02.2014 24.02.2015 | 383.22 | M/s. Structwel Designers & ConsultantsPvt.Ltd. |  |  | 6 | 1
11 | Providing and laying polymer based Geo membrane for pond lining to lakes in Golf Course at Kharghar. 02/CIDCO/EE(KHR-II)/2013-14 M/s. Ajwani Infra. Pvt. Ltd. | 21.01.2014 20.01.2015 | 144.95 | M/s. Structwel Designers & ConsultantsPvt.Ltd. |  |  | 6 | 1
12 | Maintenance of Grass Turf and landscape for Kharghar Valley Golf Course(KVGC) at Kharghar. 03/CIDCO/EE(GC)/12-13 M/s. Irrigation Products International Pvt. Ltd. | 01.06.2013 31.05.2014 | 213 | M/s Indian Register of shiping. C.A.No:- 05/CIDCO/CE(S)/ 2012-13 |  |  |  | 4
13 | Resurfacing of Roads in sector-11,12 & 15 at Kharghar,Navi Mumbai 27/CIDCO/EE(KHR-II)/13-14 M/s. Ajwani Infrastructure Pvt. Ltd. | 02.07.2014 01.11.2015 | 339.24 | M/s. Structwel Designers & ConsultantsPvt.Ltd./ C.A.No:- 02/CIDCO/SE(HQ)/ EE(NM)/2014-15 | 11.12.2014 | 14000 | 3
DIVISION : EE(KHR-III)
1 | Development of NIFT campus on plot no. 15 (2nd phase) & plot no. 20 in sector 4 at Kharghar, Navi Mumbai. M/s. Unity Infraprojects Ltd.CA.No.01/CIDCO/SE(KHR-III)/EE(KHR-IV)/2009-10 | 11.10.2010/ 10.04.2012 for plot15 & 10.10.2012/ for plot 20 30.12.2013 | 10338.55 10029.96 | Dr. Anand R.Kutti
2 | Development of Detention Pond in sector-22 at Kharghar,Navi Mumbai 09/CIDCO/EE(KHR-II)/13-14 M/s. VUB Engineers Pvt. Ltd. | 24.06.2014 23.06.2016 | 2679.61 | M/s. Structwel Designers & ConsultantsPvt.Ltd./ C.A.No:- 02/CIDCO/SE(HQ)/ EE(NM)/2014-15 | 11.12.2014 | 14000 | 8
3 | Providing Interior works for Audotorium of Gram Vikas Bhavan on plot No. 76-A in sector-21 at Kharghar,Navi Mumbai(3rd Call) M/s. Indecor Slides (I) Pvt.Ltd. Mumbai. CA.No.03/CIDCO/SE(KHR-I)/ EE(KHR-III)/2013-14 | 18.07.2014/ 17.04.2015 | 225.22 | M/s. Structwel Designers & ConsultantsPvt.Ltd./ C.A.No:- 02/CIDCO/SE(HQ)/ EE(NM)/2014-15 | 11.12.2014 | 14000 | 3
4 | Providing Interior works for main building of Gram Vikas Bhavan on plot No 76-A in sector- 21 at Kharghar,Navi Mumbai(3rd call) M/s. Sanjiv Yajnik & Associates ,Mumbai. CA.No.02/CIDCO/SE(KHR-I)/ EE(KHR-III)/2013-14 | 18.07.2014/ 17.04.2015 | 345.78 | M/s. Structwel Designers & ConsultantsPvt.Ltd./ C.A.No:- 02/CIDCO/SE(HQ)/ EE(NM)/2014-15 | 11.12.2014 | 14000 | 3
5 | Construction of Maharashtra Blood Transfusion Academy on plot No. 74,in sector-20 at Kharghar ,Navi Mumbai. |  | 568.41 (Estimated cost) | M/s. Structwel Designers & ConsultantsPvt.Ltd./ C.A.No:- 02/CIDCO/SE(HQ)/ EE(NM)/2014-15 | 11.12.2014 | 14000 | 6
6 | Construction of Glass Reinforced concrete (GRC) Pergola moulding and cladding for Gram Vikas Bhavan on plot No. 76-A in sector- 21 at Kharghar. CA.No.04/CIDCO/SE(KHR-I)/ EE(KHR-III)/2013-14 |  | 179.4 | M/s. Structwel Designers & ConsultantsPvt.Ltd./ C.A.No:- 02/CIDCO/SE(HQ)/ EE(NM)/2014-15 | 11.12.2014 | 14000 | 3
7 | Construction of Hospital Building for Regional reaserch institute of Homeopathy (RRU) on plot No. 38 & 39,in secor-18 at Kharghar,Navi Mumbai. C.A.No- 01/CIDCO/SE(KHR-I)/EE(KHR-III)/2013-14 M/s. Mahavir Road & Infrastructure Pvt.ltd. |  | 2092.25 | M/s. Structwel Designers & ConsultantsPvt.Ltd./ C.A.No:- 02/CIDCO/SE(HQ)/ EE(NM)/2014-15 | 11.12.2014 | 14000 | 8
41.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.0

## SE(HSG)
DETAILS OF THIRD PARTY QUALITY AUDITORS FOR SE(HOUSING) CIRCLE (HOUSING & INFRA WORKS)
DIVISION : EE( HSG- I & II)
Sr. No. | Name of Work / Agency / C.A. No. | Date of Start | Awarded Value / Revised Value (Rs. In Lacs) | Name of TPQA Agency / C.A.No. of TPQA work | Date of Appointment | Rate per visit(Rs) | No.of visits |  | Remarks
Date of Comple./ Extended date of Completion
[7 empty] | Planned | Actual
1 | Design and construction of MIG & HIG type tenements tenements with shops and offices at, Navi Mumbai. M/s B. G. Shirke Construction Tech. Pvt. Ltd. C. A. No. 01/CIDCO/CE & GM (T) /SE(HSG)/KHR/2011-12 . | 03.11.2011/ 12.12.2014 | 39633.28/ 48921.31 | M/s Indian Register of shiping. C.A.No:- 01/CIDCO/SE(HQ)/ EE(NM)/2012-13 | 18.09.2012 | 79900 | 29 | 26
DIVISION : EE( HSG- I )
1 | Integrated Infrastructure Development of 35 M wide road from Pandav Marg to Housing schenes in sect 36 at Kharghar CA No. 01/ CIDCO/ SE(HSG) /EE(HSG-I) /2012-13 | 07.09.2013/ 16.12.2014 | 2043.41 | M/s Certification Engineers International Limited. C.A.No:- 12/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 21.02.2014 | 27672 | 6 | 3
DIVISION : EE( HSG- III & IV)
1 | Design and construction of EWS & LIG type tenements with shops and onsite infrastructure works in sector -36 at Kharghar ,Navi Mumbai. M/s B. G. Shirke Construction Tech. Pvt. Ltd. C. A. No. 01/CIDCO/CE & GM (T) /SE(HSG)/KHR/2012-13 . | 05.02.2013 04.05.2015 31.12.2015 | 55383.87 | M/s Indian Register of shiping. C.A.No:- 05/CIDCO/SE(HQ)/ EE(NM)/2012-13 | 29.05.2013 | 125692 | 35 | 19
41.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.0

## SE(KK)
DETAILS OF THIRD PARTY QUALITY AUDITORS FOR SE(KK) CIRCLE (INFRA WORKS)
DIVISION : EE(KLM)
Sr. No. | Name of Work / Agency / C.A. No. | Date of Start | Awarded Value / Revised Value (Rs. In Lacs) | Name of TPQA Agency / C.A.No. of TPQA work | Date of Appointment | Rate per visit(Rs) | No.of visits |  | Remarks
Date of Comple./ Extended date of Completion
[7 empty] | Planned | Actual
1 | Upgradation of internal roads in Sector - 1 to 11 in KRC at Kalamboli. M/s.Swastik Infra Logic (I) Pvt. Ltd. C.A.No.11/CIDCO/EE(KLM-I)/2012-13 | 04.02.13 31.03.14 | 475.81/ 582.93 | M/s Indian Register of shiping. C.A.No:- 10/CIDCO/CE(S)/2013-14 | 13.02.2014 | 26200 | 1 | 1
2 | Upgradation of internal roads in Sector - 12 to 15 in KRC at Kalamboli. M/s.Swastik Infra Logic (I) Pvt. Ltd. C.A.No.12/CIDCO/EE(KLM-I)/2012-13 | 04.02.13 31.03.14 | 452.50/ 463.46 | M/s Indian Register of shiping. C.A.No:- 10/CIDCO/CE(S)/2013-14 | 13.02.2014 | 26200 | 1 | 1
3 | Upgradation of internal roads in Sectors 1E to 6E in KRC at Kalamboli. M/s.Swastik Infra Logic (I) Pvt. Ltd. C.A.No.14/CIDCO/EE(KLM-I)/2012-13 | 04.02.13 31.03.14 | 329.66/ 343.76 | M/s Indian Register of shiping. C.A.No:- 10/CIDCO/CE(S)/2013-14 | 13.02.2014 | 26200 | 1 | 1
4 | Upgradation of peripheral roads in Kalamboli Warehousing Complex at Kalamboli, Navi Mumbai. Agency : M/s J.M. Mhatre Infra.Pvt.Ltd. CA No.09/CIDCO/EE (KLM-I)/2011-12. | 06.12.2012 05.12.14 Extension in time period is in process | 6066.35/ 7638.93 | IIT MUMBAI | 19.12.2012 | 13,93,000.00 (Total Lump sum Amnt) | 30 | 13
DIVISION : EE(KMT)
1 | Construction of prayer hall & Burial ground in Sect-32 at Kamothe C.A. No – 05/CIDCO/EE(KMT)/12-13 Agency – M/S. Thakur Infra Pvt.Ltd | 21.10.13 | 65 | M/s. Certification Engineers International Ltd. | 04.04.2014 | 24999 | 2 | 2
2 | Construction of Hawkers market in Sec-24 at Kamothe C.A. No. 01/CIDCO/EE(KMT) /12-13 Agency –M/S. R. K. Patil | 21.05.13 | 143.43 | M/s. Certification Engineers International Ltd. | 04.04.2014 | 24999 | 2 | 2
41.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.0

## SE(Vashi
DETAILS OF THIRD PARTY QUALITY AUDITORS FOR SE(VASHI) CIRCLE (INFRA WORKS)
DIVISION : EE(Vashi)
Sr. No. | Name of Work / Agency / C.A. No. | Date of Start | Awarded Value / Revised Value (Rs. In Lacs) | Name of TPQA Agency / C.A.No. of TPQA work | Date of Appointment | Rate per visit(Rs) | No.of visits |  | Remarks
Date of Comple./ Extended date of Completion
[7 empty] | Planned | Actual
1 | Construction of Sagari Police Station (NRI) cumTraffic Police Chowky on plot no.05, Sector 15A in CBD Belapur, Navi Mumbai. Agency: M/s. Thakur Infraprojects Pvt. Ltd. C.A.No. 01/CIDCO/SE (D)/EE(NL)/2012-13 | 28.12.2012/ 27.12.2014 | 422.67 | M/s. Certification Engineers International Ltd. C.A.No. 14/CIDCO/SE(HQ)/EE (NM)/2013-14 | 06.05.2014 | 24900 | 6 | 5
2 | Providing Integrated Infrastructure works in sector-15 at Ghansoli,Navi Mumbai Agency: M/s. Ajwani Infrastructure Pvt. Ltd. C.A.No. 01/CIDCO/EE(Vashi)/ 2014-15 | 25.11.2014/ 24.05.2016 | 399.06 | New work |  |  | 10
3 | Facility Management services for comprehensive operation & maintenance of Agri Koli Shanshkrutik Bhavan in sector-24 at Nerul,Navi Mumbai(4th call) Agency: M/s. BVG India Ltd. C.A.No. 06/CIDCO/SE(V/VV)/EE(Nerul)/ 2012-13 | 01.01.2015/ 31.12.2017 | 278.54 | New work |  |  | 40
41.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.0

## SE(NT)
STATUS OF THIRD PARTY QUALITY AUDITORS FOR SE(NT) CIRCLE (INFRA WORKS)
DIVISION : EE(Aur-I)
Sr. No. | Name of Work / Agency / C.A. No. | Date of Start | Awarded Value / Revised Value (Rs. In Lacs) | Name of TPQA Agency / C.A.No. of TPQA work | Date of Appointment | Rate per visit(Rs) | No.of visits |  | Remarks
Date of Comple./ Extended date of Completion
[7 empty] | Planned | Actual
1 | P&L sewerline network near LIG,MIG housing scheme, outside Growth centre at Nagar-I, CIDCO, Waluj Mahanagar. Agency: M/s. Sunrise Construction C.A.No. 09/CIDCO/EE(AUR)/ 2012-13 | 17.07.2013/ 16.01.2015 | 293.39 | M/s. Certification Engineers International Ltd. C.A.No. 10(A)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 7 | 4
2 | Asphalting of WBM roads in Nagar-I, CIDCO, Walunj Mahanagar. Agency: M/s. GNI Infrastructure Pvt.Ltd. C.A.No.02/CIDCO/EE(AUR-I)/ 2013-14 | 21.08.2014/ 20.08.2015 | 630.74 | M/s. Certification Engineers International Ltd. C.A.No. 10(A)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 5 | 3
3 | Resurfacing to major roads in Growth Centre of Nagar-I, CIDCO, Waluj Mahanagar. Agency: M/s. Chandan Engineers C.A.No. 10/CIDCO/EE(AUR)/ 2012-13 | 25.07.2013/ 24.04.2014/ 03.06.2014 | 168.01 | M/s. Certification Engineers International Ltd. C.A.No. 10(A)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 4 | 3
4 | Construction of roads upto WBM standard in Growth Centre-II of Nagar-II, CIDCO Waluj Mahanagar. Agency: M/s. Ray Construction C.A.No. 06/CIDCO/EE(AUR)/ 2012-13 | 01.03.2013/ 28.02.2014/ 10.05.2014 | 202.61 | M/s. Certification Engineers International Ltd. C.A.No. 10(A)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 5 | 4
5 | P & L balance work of underground sewerage network & making individual house connection for Ambad city Dist. Jalna. Agency: M/s. Sunrise Construction C.A.No. 01/CIDCO/EE(AUR)/ 2013-14 | 21.11.2013/ 20.11.2014 | 336.24 | M/s. Certification Engineers International Ltd. C.A.No. 10(A)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 5 | 4
5 | P & L balance work of underground sewerage network & making individual house connection for Ambad city Dist. Jalna. Agency: M/s. Sunrise Construction C.A.No. 01/CIDCO/EE(AUR)/ 2013-14 | 21.11.2013/ 20.11.2014 | 336.24 | M/s. Certification Engineers International Ltd. C.A.No. 10(A)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 5 | 2
DIVISION : EE(Aur-II)
1 | Construction of 15m, 18m & 24m wide roads upto WBM standard in balance part outside Growth centre at nagar-I, CIDCO, Waluj Mahanagar. C.A.No-08/CIDCO/EE(AUR)/ 2012-13 Agency :- M/s. | 17.07.2013/ 16.01.2015 | 298.38 | M/s. S.G.S. India Pvt. Ltd. C.A.No. 10(B)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 7 | 4
2 | Asphalting & resurfacing of roads at various locations in Nagar-I, CIDCO, Waluj Mahanagar. Agency: C.A.No. 01/CIDCO/EE(AUR-II)/2013-14 | 04.09.2014/ 03.06.2015 | 162.17 | M/s. S.G.S. India Pvt. Ltd. C.A.No. 10(B)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 4 | 1
3 | Providing, supplying, lowering, laying & jointing D.I. water supply lines to balance portion outside Growth Centre at Nagar-I, CIDCO, Waluj Mahanagar. C.A.No. 02/CIDCO/EE(AUR-II)/2013-14 | Tender recalled | 318.26 | M/s. S.G.S. India Pvt. Ltd. C.A.No. 10(B)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | Tender recalled
4 | Replacement of balance A.C. water supplylines with D.I. water supplylines outsidde Growth Centre at Nagar-I, CIDCO, Waluj Mahanagar. Agency: M/s. A.G.Mapari C.A.No. 03/CIDCO/EE(AUR- II)2013-14 | 31.01.2014/ 30.07.2014 | 118.58 | M/s. S.G.S. India Pvt. Ltd. C.A.No. 10(B)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 3 | 2
5 | P & L sewer line network outside Growth Centre Nagar-I, CIDCO, Waluj Mahanagar (Phase-II). Agency: M/s Sunrise Construction C.A.No. 04/CIDCO/EE(AUR-II)/2013-14 | 24.02.2014/ 23.08.2014 | 424.57 | M/s. S.G.S. India Pvt. Ltd. C.A.No. 10(B)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 7 | 3
6 | Providing, supplying, lowering, laying & jointing D.I. water supply lines outside Growth Centre, Nagar-I, CIDCO, Waluj Mahanagar. Agency: M/s. A.G.Mapari C.A.No. 07/CIDCO/EE (AUR)/ 2013-14 | 16.07.2013/ 15.01.2014 | 123.04 | M/s. S.G.S. India Pvt. Ltd. C.A.No. 10(B)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 2 | 2
7 | Replacing of A.C.water supply lines with D.I. water supply lines in Growth Centre & Housing scheme at Nagar-I, CIDCO, Mahanagar. Agency: M/s A.G.Mapari C.A.No. 04/CIDCO/EE(AUR)/ 2012-13 | 3.01.2013/ 10.05.2014 | 232.49 | M/s. S.G.S. India Pvt. Ltd. C.A.No. 10(B)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 2 | 2
8 | Construction of 18 m wide link road & providing storm water drain between Nagar-II & Nagar-IV ,Waluj Mahanagar,CIDCO Waluj Mahanagr Agency:- M/s. Chandan Engineer & contractor C.A.No. 04/CIDCO/EE(AUR)/ 2012-13 | 3.01.2013/ 10.05.2014 | 377.48 | M/s. S.G.S. India Pvt. Ltd. C.A.No. 10(B)/CIDCO/SE(HQ)/ EE(NM)/2013-14 | 11.03.2014 | 35000 | 4
41.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.0

## SE(Elect)
DETAILS OF THIRD PARTY QUALITY AUDITORS FOR SE(ELECT) CIRCLE (INFRA WORKS)
DIVISION : EE(Elect-I)
Sr. No. | Name of Work / Agency / C.A. No. | Date of Start | Awarded Value / Revised Value (Rs. In Lacs) | Name of TPQA Agency / C.A.No. of TPQA work | Date of Appointment | Rate per visit(Rs) | No.of visits |  | Remarks
Date of Comple./ Extended date of Completion
[7 empty] | Planned | Actual
1 | Development of power supply infrastructure distribution network including construction of 33/11KV & 11/0.4KV HT substations & allied electrical work in sector-25 to 45, Kharghar Node, Navi Mumbai (Phase-I). M/s. IVRCL Ltd. CA No.12/CIDCO/EE(Elect-I)/2011-12 | 30/08/2012 to 29/08/2014 Extension proposed upto 27/02/2015 | 6097.74 | M/s. Certification Engineers International Ltd., C.A.No-03/CIDCO/CE(South)/ 2013-14 | 16.01.2014 | 19100 | 10 | 7
DIVISION : EE(Elect-II)
1 | Development of power supply infrastructure distribution network including 33 kv substation equipment & construction of 11/0.4 kV H.T Substation & allied electrical works in Ulwe Node, Navi Mumbai (Phase –I). Name of Agency : M/s. Leena Powertech Engineers Pvt. Ltd C.A. No. 12/CIDCO/EE(Elect-II)/2011-12 | 29-01-2013 / 28-01-2014 | 4487.00/ 4706.00 | M/s. Certification Engineers International Ltd., C.A.No-02/CIDCO/CE(South)/ 2013-14 | 16.01.2014 | 27006 | 15 | 8
41.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.01.0